## Sheet1
Question 1
When should the project plan be updated? (choose the best answer)
After the Daily Scrum to ensure an accurate daily overview of project progress.
The project plan must be updated before to the Daily Scrum.
Before the Sprint Planning to know how much work will have to be done in the Sprint.
The Product Backlog is the plan in Scrum. It is updated as new information and insights emerge.
Resources
Question - Product Backlog management
Domain
Product Backlog Management
Question 2
A separate Product Owner and Product Backlog is needed for every: (choose the correct answer)
Project
Product
Portfolio
Program
Resources
Question - How many Product Owners?
Domain
Scrum Team
Question 3
In the context of Scrum, how should budgeting and financial forecasting be approached? (choose the best two options)
Budgeting is unnecessary since the only required funding pertains to the operational costs of Scrum Teams.
Regularly examine the results of delivered Sprint Increments to assess the value produced relative to the investment made.
Scrum is incompatible with traditional accounting practices, so the finance department should allocate a fixed cost per Sprint for each team.
Fund a single release through multiple Sprints, with each Sprint delivering shippable increments.
Establish a fixed budget and guarantee that the project is completed on schedule, within the defined scope, and adhering to the budget.
Resources
Question - Budgeting for a new feature
Domain
Product Planning
Question 4
After examining your product's customer base, you discover that various customer types utilize your product in distinct ways. Given this insight, what is the best thing to do? (choose the best answer)
Retain a single product, ensuring that each release caters to every customer type.
Consider developing separate products tailored to the needs of each customer type.
Take no action; focus on new features to attract new customers and boost sales.
Maintain a single product but adopt different marketing strategies for each customer type.
Resources
Question - Different user groups
Domain
Product Planning
Question 5
Managing the Product Backlog involves which of the following? (choose all that apply)
Ordering the items.
Forecasting the effort required of Product Backlog items.
Reviewing the Product Backlog items with stakeholders.
Breaking large Product Backlog items into multiple smaller Product Backlog items.
Reducing or ideally eliminating dependencies between items
Resources
Question - Managing backlog items
Domain
Product Backlog Management
Question 6
When a user's expectations of a product are not met, meaning their desired experience does not meet their actual experience, this is described as... (choose the best answer)
Unattainable user expectations.
Expectation experience drift.
The user satisfaction gap.
A product failure.
Resources
Question - User Satisfaction
Domain
Stakeholders and Customers
Question 7
After a recent big release, you as the Product Owner look at the usage data per feature, new and old. To your surprise the data reveals that several features you and your stakeholders deemed crucial are actually among the least used by your customers. What steps would you take to investigate this situation? (select all that apply)
Consider removing the features that have never been used.
Engage with some of your users to gain a better understanding of their needs.
Conduct further analysis on the newly released features to determine if developers implemented them correctly.
Design an experiment to identify the features users perceive as valuable.
Immediately remove the least-used features.
Resources
Question - New features are not being used
Domain
Product Planning
Question 8
As a Product Owner, you are faced with multiple stakeholders, each with at least one feature they consider crucial for the next release. You have verified that these feature requests are valid and could enhance your product. What is the best course of action? (Choose the best answer)
Delay the release until all essential features are completed and integrated into the product.
Escalate the situation to the steering committee for a decision.
Prioritize the needs of the two most influential stakeholders and release once their requirements are met.
Release the product once you can deliver at least one valuable outcome, even if not all features have been implemented.
Resources
Question - Conflict management, release frequency
Domain
Release Planning
Question 9
Which two Scrum Values are primarily impacted when an individual or team switches tasks or encounters interruptions often? (choose the best two answers)
Openness.
Commitment.
Courage.
Respect.
Focus.
Resources
Question - Task Switching
Domain
Scrum Values
Question 10
Who is accountable for ensuring the Product Goal is communicated and maintained? (choose the best answer)
Executive Sponsors.
The Product Owner.
All of the above.
Stakeholders.
The Developers.
Resources
Question - Product Goal
Domain
Product Vision
Question 11
If the Product Owner is struggling to find time to complete all of his/her work, what can he/she do to ensure the Product Owner accountabilities are met? (choose the best answer)
None of the above
All of the above.
Divide the Product Owner role into ﾓBusiness Product Ownerﾔ and ﾓTechnical Product Owner" roles to share the work.
Delegate tasks to Developers, like detailing Product Backlog items, interviewing users, and analyzing data.
Reduce the product into components, and assign a Product Owner to each, then assume the role of ﾓChief Product Ownerﾔ responsible for the integrated product.
Resources
Question - Product Owner delegation
Domain
Product Backlog Management
Question 12
You work for a bank that has many financial products such as investment funds, credit cards, high interest savings accounts and more. The issue is, when one of these products changes it impacts the return on investment (ROI) and this has a knock on effect to the other products the bank offers as investors compare ROI between the products. What can you do to reduce this issue?(choose the best answer)
Form products that are as independent as possible and let each product determine their own release plans, but ensure coordination.
Appoint one Product Owner to oversee all the products.
To ensure consistency, create a centralized and coordinated multi-product development plan.
Ensure that the Program Office manages all releases of all products.
All of the above.
Resources
Question - Own release plans
Domain
Release Planning
Question 13
The smallest amount of progress that can still be considered valuable enough to be released is one that: (choose the best option)
Delivers a single new or improved outcome.
Fixes at least one defect.
Adds a new feature.
Delivers all Sprint Backlog items.
Resources
Question - Minimum increment
Domain
Release Planning
Question 14
When should the Scrum Team do Product Backlog refinement? (choose the best 2 answers)
Business Analysts will do the refinement work for the Scrum Team, usually 1- 2 Sprints ahead of the development Sprints.
The Product Owner takes the time between the Sprints to do it.
During any Sprint as needed, ideally in advance of the upcoming Sprint.
It must be done by Sprint 0.
In the current Sprint if they have been unable to do it in preceding Sprints.
Resources
Question - When to do product backlog refinement
Domain
Product Backlog Management
Question 15
What will the Product Owner most likely be doing during the Sprint? (choose be best 3)
Reordering items in the Product Backlog.
Running the Daily Scrum.
Answer questions from the Developers about items in the current Sprint.
Prioritizing the Developers tasks in the Sprint Backlog.
Gathering more information and opinions from stakeholders.
Updating the Sprint burndown chart.
Resources
Question - Product Owner During a Sprint
Domain
Scrum Team
Question 16
Why would you consider reducing investment in a product? (choose the best option)
None of the above.
When the Unrealized Value is extremely high.
When the Current Value is extremely low.
When the Unrealized Value is extremely low.
When the Current Value is extremely high.
Resources
Question - Decrease Investment
Domain
Budgeting
Question 17
You are an experienced Product Owner and team leader. You want to ensure your vision inspires and creates motivation. Which of the below elements might you included in the Product Vision and strategy to maintain enthusiasm for the product among stakeholders? (choose all that apply)
A description of what value the product brings to the users and how it can be measured.
A description of how the product will generate revenue.
A description of how the product competes against others in the market.
A description of how your product will be used to achieve outcomes.
A description of the product's users and what they want to achieve.
Resources
Question - Attributes of a good Product Vision
Domain
Product Vision
Question 18
Your company is trying to raise venture capital. Your CEO has asked you to speak with a potential stakeholder investor. This person wants to see data to assess the value your product is delivering. Which measures might give insight into this? (choose all that apply)
The weekly velocity of the Developers.
The average selling price as compared to close competitors.
Product profitability.
Market Share.
Revenue per Employee.
Resources
Question - Product Value for an investor
Domain
Product Value
Question 19
In order to justify the price increase of a product, your primary objective should be to (choose the best answer)
Improve the value experienced by the customer.
Lower the price temporarily before raising it higher than the original.
Reduce the number of features to improve ease of use.
Enhance the product by adding more features.
Resources
Question - Price increase
Domain
Business Strategy
Question 20
The company you work for desperately needs to boost the market share of one of its key products. The sales department is urging for a price reduction to lure more customers with attractive prices, while the accounts department is worried about a potential loss of profitability with reduced prices. What are the top four sources of information to consider when evaluating the sales leader's proposal to reduce the price?
Examination of customer satisfaction levels.
Company's earnings targets.
Competitor pricing analysis.
Assessment of the channel sales strategy.
Market share analysis.
Identification of unaddressed customer needs.
Resources
Question - Should you reduce the price?
Domain
Product Planning
Question 21
If Product Backlog items are not clear during Sprint Planning what might happen? (choose the best 2 answers)
There will be no impact on Sprint Planning or the Sprint.
The team cancel the meeting so backlog refinement can be done first.
The Developers will have difficulty creating a forecast of work for the Sprint without more clarity.
Sprint Planning will take longer as the Product Owner needs to explain backlog items.
Nothing, so long as the Product Owner gives the Developers a clear Sprint Goal.
The Scrum Master has failed, the Scrum Master is changed and the Sprint is re-started.
Resources
Question - Unclear Backlog Items
Domain
Empiricism
Question 22
Why does Agile insist on frequent product releases? (choose the best option)
They enable teams to inspect and adapt more frequently.
None of the above.
They help teams to learn how to correct and eliminate errors.
Smaller, more frequent releases are less risky.
They help teams better understand and meet customer needs.
All of the above.
Overall explanation
See the video on release frequency in the Release Planning section if the explanation video for this one does not load below (I am experiencing a bug with Udemy for this one). Let me know if the problem persists.
Resources
Question - Release frequency
Domain
Empiricism
Question 23
You have a furniture company that manufactures multiple products. You are considering the allocation of new investment funds for 2 products in particular. Product A has a wider target audience but experiences lower customer satisfaction, and Product B currently generates higher revenue. Given this information, which of the below investment approaches would you pick?
All of the above.
Invest in Product A to enhance its market share, customer satisfaction, and revenue generation.
Initially invest in both equally, regularly evaluating the effects of new investments and marketing campaigns for both products.
Explore increasing marketing efforts for Product B to grow its market share.
Resources
Question - Product A and B for target markets
Domain
Product Planning
Question 24
Which two Key Value Areas are primarily impacted when an individual or team switches tasks or encounters interruptions often? (choose the best two answers)
Ability to Innovate.
Unrealized Value.
Current Value.
All of the above
Time to Market.
Resources
Question - Task Switching KVM
Domain
Product Planning
Question 25
Your organization has recently adopted Scrum. Management seeks to quantify the benefits gained by Scrum thus far. Which metrics are most useful in assessing if value is being delivered in terms of the features released and the organizations' adoption of Scrum. Which two metrics would be most suitable? (choose the best two options)
Work efficiency.
Time to market.
Expenditure.
Customer satisfaction.
Team velocity.
Resources
Question - Value to the customer
Domain
Product Planning
Question 26
Burndown charts are a visual aid to showing progress, what does it track? (choose the best option)
Accumulated business value delivered to the customer.
Individual worker productivity.
Work remaining across time.
Accumulated cost.
Resources
Question - Burndown trendline
Domain
Forecasting
Question 27
The Sprint Backlog represents the Sprint forecast, but what is the best description of a Sprint forecast? (choose the best answer)
A commitment by the Developers to deliver a particular set of Product Backlog items.
Useful for the stakeholders to know what tasks individual Developers are responsible for.
The amount of work the Developers believe they can complete in that Sprint.
A tool for management to monitor team performance and capacity.
Resources
Question - What is a Sprint forecast?
Domain
Forecasting
Question 28
Over the last few Sprints the Developers have struggled to get all their forecasted work done to meet the Sprint Goals. What should the Product Owner do to help the Developers to improve their forecasting for the next few Sprints? (choose all that apply)
Ask the Scrum Master to show the Developers techniques for improving their ability to forecast work.
The Product Owner should spend more time with the Developers.
Add more Developers to the team so they can get more done.
Change low performing Developers for high performers.
Bring this up in the next Sprint Retrospective to discuss why this happens and what changes will help to fix it.
Resources
Question - Developer Forecasting
Domain
Release Planning
Question 29
Which of the below are mandatory in Scrum? (choose all that apply)
Critical Path Analysis.
Project Gantt chart.
None of the above.
Feature burn-up.
Refactoring.
Burndown chart.
Resources
Question - Are Burndown charts required in Scrum?
Domain
Scrum Artifacts
Question 30
What are the key advantages of a Product Owner sharing a well-defined Product Vision and ensuring everyone understands it properly? (select the top three answers)
A Product Vision enables the Sprint Review to assess incremental progress effectively.
A Product Vision is not compulsory in Scrum, and it doesn't provide any direct advantages.
It keeps the Scrum Team focused and offers a reference point for their decisions.
A Product Vision helps the Scrum Team to commit to completing the remaining work in the Product Backlog.
A Product Vision offers a comprehensive direction, ensuring that Sprints deliver significant value.
Resources
Question - Clear Vision Benefits
Domain
Product Vision