## Sheet1
Question 1
Which of the following would be wrong for a Product Owner to do? Select the best answer.
Determine the timing for releasing the product Increment.
Approve the work completed during the Sprint.
Set the Sprint Goal without consulting the team.
Set a Product Goal.
Resources
Question - What the Product Owner should not do
Domain
Scrum Artifacts
Question 2
As a Product Owner in scaled Scrum with multiple Scrum teams, what approach would be most beneficial when you are unable to dedicate enough time to each team?(choose the best option)
Assemble a group of Proxy Product Owners from the current Scrum Team members.
Ensure all Scrum Teams have a thorough grasp of the Product Vision, so they can be guided by it if you delegate certain tasks to the Developers.
All the above options are valid; the decision depends on the specific situation.
Hire additional Product Owners for every product component.
Collaborate with the Program Management Office to receive the necessary support.
Resources
Question - Delegation
Domain
Product Vision
Question 3
As the Product Owner you realise the last increment did not meet the full Definition of Done and you are concerned about its quality. What is the likely result? (choose all that apply)
The next Sprints velocity may be interrupted when quality issues are encountered.
The indication of progress on the Product Backlog is not transparent.
The project manager cannot effectively update the plan.
The incomplete Sprint Backlog items should be returned to the Product Backlog.
The Increment should not be released.
Resources
Question - When the Definition of Done is not met
Domain
Scrum Artifacts
Question 4
The Developers in the company you work at complain that they feel frustrated by constant interruptions and useless meetings, and much of their past work has resulted in being unneeded. You notice that some of your best Developers are leaving. What measurements should you consider for informing you on how to improve employee retention rates? (choose the best answer)
The Innovation Rate, which is the ratio of new work to total work.
All of the above.
The On-Product Index, which measures the proportion of work related to the product to total work.
Employee Net Promoter Scores, which measures the overall job satisfaction and company satisfaction of the developers.
Resources
Question - Employee retention
Domain
Scrum Values
Question 5
Which of the following are true about Scrum? (Select all that apply).
Each element of Scrum serves a distinct purpose and is crucial for the successful application of Scrum in building complex products.
Scrum is similar to traditional processes, with the key difference being self-management replacing Project Managers.
Scrum is a methodology that allows you to selectively implement components based on your organization's specific needs.
Scrum is founded on the principles of empiricism.
Scrum is a framework designed to deliver value through adaptive solutions for complex problems.
Resources
Question - What are the advantages of Agile?
Domain
Business Strategy
Question 6
Who has accountability for clearly expressing the Product Backlog Items?(choose the best answer)
The Scrum Master, with the option to enlist the Product Owner's assistance.
The Scrum Master, with the option to enlist the Developers' assistance.
The Product Owner, who can designate a team member within the Scrum Team to handle the task.
The Scrum Master.
The Developers.
Resources
Question - Accountable for the backlog being clear
Domain
Product Backlog Management
Question 7
Scrum is about getting started, the right product will emerge eventually. True or False?
FALSE
TRUE
Resources
Question - Just get started
Domain
Product Backlog Management
Question 8
In Scrum every .... needs a Product Owner. Choose from the below to fill in the blank.
Program
Product
Portfolio
Project
Overall explanation
In Scrum every Product should have a Product Owner. Only one Product Owner and one Product Backlog. It may have multiple Scrum Teams (such as in a Nexus), but only ever one Product Owner and Backlog.
Resources
Question - How many Product Owners?
Domain
Scrum Team
Question 9
Who tells the Developers how to turn Product Backlog items into Increments of value?
The Product Owner
The Scrum Master
None of the above
The Lead Developer
Resources
Question - Who determines how Developers do their work?
Domain
Scrum Team
Question 10
If Sprint Backlog items are not clear what might be the concerns? (choose the best 4 answers)
Development time might be wasted.
The Scrum Master has failed, the Scrum Master is changed and the Sprint is re-started.
There is no concern, the Developers do not need the items to be clear.
The team might have different understandings and different basis for adaptation.ﾠ
Decisions made on those items may be bad decisions.
The Developers will have difficulty creating a forecast of work for the Sprint without more clarity.
Resources
Question - Backlog Refinement
Domain
Empiricism
Question 11
Which is the best description of the Sprint Backlog as a result of Sprint Planning? (choose the best answer)
It is a decomposition of Product Backlog items such that enough work is decomposed for at least the first days of the Sprint.
It is an exhaustive list of all tasks for the Sprint.
It is a list of the User Stories estimated in story points, and a list of corresponding tasks that are estimated in hours.
It is a task list where every Developer has signed up for all the tasks that they intend to do in the Sprint.
It must be ordered by the Product Owner.
Resources
Question - Sprint Backlog Definition
Domain
Scrum Artifacts
Question 12
Upon discovering that several features considered important have low usage, what actions should a Product Owner take to investigate this issue? (choose all that apply)
Examine whether underutilized features effectively address the intended problem.
Carry out experiments to gain a better understanding of what customers value.
Spend more time communicating with users to sell the benefits of the features.
Disable seldom-used features and collect feedback.
Overall explanation
This question in essence is the same as the one in the below video.
Spending time communicating the benefits of the feature is the wrong order of business. Scrum advocates for Product Owers to first understand the customer needs and then produce a product that meets those needs. Producing a Product or features that the customer doesn't initially want only to advertise the benefits later hoping the advertising campaign works is a very risky strategy.
Carrying out experiments to better understand what customers value is an empirical way of doing things and much less risky.
Examining if the underutilized features actually address the intended problem is a good idea. It may be that you remove those features for simplicity. Simplicity of use for the user, and less to maintain for the developers.
Just be aware there may be questions that ask about removing underused features, and never used features. If the feature has never been used then it is safe to remove it, as it will have no impact on any users. however, if it is seldom used then only remove the feature after consideration. It could be that some users really need that feature and at least need a warning about its upcoming removal.
Resources
Question - New features not being used
Domain
Empiricism
Question 13
A new social media app has entered the market and is starting to steal customers away from your company's primary social media product. Your competition releases new and useful features quicker than you can and their customers are more satisfied. You realise you need to improve your T2M. How can you do this? (choose all that apply)
Taking control of and improve the delivery pipeline.
Reducing the number of features in each product release.
Use automation to improve speed.
Removing internal communication bottlenecks.
Removing activities that do not add value to the development and delivery process.
Resources
Question - Improving time to market 2
Domain
Release Planning
Question 14
The Scrum Master is inexperienced and suggests that Developers with rare skills should be involved with multiple Scrum teams. Which are likely outcomes from such a decision? (choose all that apply)
Teams may become ﾓbottleneckedﾔ waiting for key Developers.
Employee costs are lower since expensive skilled employees are shared.
Teams will not be cross-functional.
Dependencies are created.
More work gets done since people with specialisms are better utilized.
Resources
Question - Cross-functional
Domain
Scrum Team
Question 15
A "cone of uncertainty" can be used for? (choose the best answer)
Determining whether to cut quality, similar to the "Iron Triangle" of project management.
Rapidly identifying and prioritizing all uncertainties.
Visualizing the uncertainty of the potential value that a Scrum Team delivers over time.
Representing the relative level of difficulty for predicting the velocity of individual team members.
Resources
Question - Cone of Uncertainty
Domain
Forecasting
Question 16
Managing the Product Backlog involves which of the following? (choose all that apply)
Ordering the items by priority.
Reviewing the Product Backlog items with stakeholders.
Breaking large Product Backlog items into multiple smaller Product Backlog items.
Forecasting the effort required of Product Backlog items.
Reducing or ideally eliminating dependencies between items
Resources
Question - Managing backlog items
Domain
Scrum Artifacts
Question 17
The user satisfaction gap is the difference between … (choose the best two answers)
The current market share of the product.
The total market size.
The user's actual experience.
The user's desired experience.
Resources
Question - What is the User Satisfaction Gap
Domain
Stakeholders and Customers
Question 18
If you are uncertain about customer needs and what the market wants, what should you do? (choose the best two answers)
Consider developing a different product.
Spend more time on validating your customer need assumptions.
Release often with smaller releases.
Spend more time creating a risk management plan.
Resources
Question - Uncertain about customer needs
Domain
Release Planning
Question 19
Why does Agile insist on frequent product releases? (choose the best option)
All of the above.
They enable teams to inspect and adapt more frequently.
Smaller, more frequent releases are less risky.
They help teams better understand and meet customer needs.
None of the above.
They help teams to learn how to correct and eliminate errors.
Resources
Question - Release frequency
Domain
Empiricism
Question 20
Which statement is the best description of the Sprint Review? (Choose the best answer)
A chance to evaluate the Sprint's outcome and decide on future adjustments.
A showcase of the functionality accomplished in the Sprint.
An examination of the work completed by the Developers during the Sprint.
A meeting to retrospectively analyze the team's performance during the Sprint.
A planning session to decide on the scope of work for the next Sprint.
Resources
Question - Sprint Review Facts
Domain
Empiricism
Question 21
You are put in a difficult position by the Executive team. Your product is losing paying customers. The CEO believes new features delivered at a quicker rate will bring customers back. The marketing executive thinks the loss of customers is down to a shrinking market and increasing new feature releases will not make much difference at this point. Which action might you take? (choose the best answer)
Collaborate with the Executive team to run a small experiment to make an informed decision.
Agree with the CEO and add features to the Product Backlog as it might increase your customer base.
Suggest voting to the stakeholders to decide which options should be considered.
Acknowledge the views of the CEO but decline to add more features to the product.
Resources
Question - Difficult Stakeholder, Experiment
Domain
Release Planning
Question 22
A new social media app has entered the market and is starting to steal customers away from your company's primary social media product. After studying this competition you realize they release new and useful features quicker than you can and their app store star rating is higher than yours. What is your best course of action? (choose the best option)
Improve your time to market and ability to innovate to respond faster.
Decrease your product price to make it more appealing.
Shift your product to a market with less competition.
Enhance your next release with new features to improve current value, retain users and attract new ones.
Resources
Question - Improving time to market
Domain
Release Planning
Question 23
A new Scrum team has been ineffective at forecasting the effort required for their Sprint Backlog items. Due to items taking longer than predicted, they fear they will not be able to meet the Sprint Goal and inform yourself as the Product Owner. What first action should you take? (choose the best first option)
Inform management that more resources are needed.
End the Sprint, since the goal cannot be achieved.
Change the Sprint Goal to match what the Developers can deliver.
Skip Product Backlog refinement activities, to gain more development time in the Sprint.
Try to reduce the scope of the Sprint, if possible, to still meet the Sprint Goal.
Resources
Question - Sprint Problems during the Sprint
Domain
Forecasting
Question 24
During Sprint Planning the Product Owner insists on a large scope for the Sprint Goal. The Backlog items chosen are getting greater than the Developers believe they can meet in the Sprint. Which actions should be taken? (choose all that apply)
Change or remove selected Product Backlog items whilst considering the Sprint Goal.
Do not start the Sprint and take a pause between Sprints to work on backlog refinement.
The Developers ensure that the Product Owner is aware, start the Sprint and monitor progress.
Ask the Developers to work overtime for this Sprint and promise that it will not happen again.
Start the Sprint and recruit additional Developers to help.
Resources
Question - Sprint Problems at Sprint Planning
Domain
Forecasting
Question 25
During the Sprint, what will the Product Owner be doing? (choose the best 3)
Gathering more information and opinions from stakeholders.
Updating the Sprint burndown chart.
Answer questions from the Developers about items in the current Sprint.
Running the Daily Scrum.
Reordering items in the Product Backlog.
Prioritizing the Developers tasks in the Sprint Backlog.
Resources
Question - Product Owner During a Sprint
Domain
Scrum Team
Question 26
Which of the below are true regarding the Product Backlog? (choose the best two answers)
All Product Backlog items must be expressed as user stories.
All Product Backlog items must be identified before the first Sprint begins.
Only the Product Owner can place items on the Product Backlog.
The Product Backlog represents the input of all stakeholders and eliminates any need for the Developers to speak to stakeholders.
The Product Backlog is ordered by the Product Owner.
The Product Backlog should be visible to the Scrum Team and stakeholders.
Resources
Question - Product Backlog Truths
Domain
Product Backlog Management
Question 27
As the Product Owner you monitor and share your product usage dashboard which shows usage rate by feature. The data shows a particular feature is seldom used. An influential stakeholder disputes the data, and insists that the particular feature is essential, despite indicated low usage rates. The stakeholder believes that measuring feature usage is a waste of time, as it is obvious that the feature should be useful. You have confirmed that the data is accurate. What should you do? (choose the best answer)
Stop measuring feature usage to please the stakeholder.
Continue measuring feature usage and use it to inform your decisions, but do not publish it.
Remove the feature.
Keep measuring and openly share the data for transparency, and use it for decision-making.
Resources
Question - Difficult stakeholder - keep measuring
Domain
Empiricism
Question 28
You release a feature that came from requirements provided to you from a key stakeholder. You find that the feature does not actually get used. You suspect the key stakeholder and other stakeholders do not understand the needs of the users as much as they think. Should you discuss this with them? (choose the correct answer)
Yes. They should realise their association with wasted effort.
No. You should show that the feature hasn't been used yet, but suggest it might be used in the future.
No. Look for new users who need this feature.
Yes. If you share what you learned from the release, it may help them improve their understanding and ability to research what users actually need.
Resources
Question - Difficult Stakeholder Knowledge share
Domain
Stakeholders and Customers
Question 29
Your organization has recently adopted Scrum. Management want to know which metrics are most useful in assessing how valuable the users find the product. Which two metrics would be most suitable?(choose the best two options)
Number of features released per month
Customer satisfaction.
On-time release ratio.
Team velocity.
Frequency of use per feature.
Resources
Question - KVA Value of Scrum
Domain
Product Planning
Question 30
How much information is actually needed to start a Sprint? (choose the best answer)
Enough so the Developers can create a forecast of what they can do during the Sprint.
Just enough to understand the design and architecture.
Just enough tasks for the Scrum Master and Product Owner to be confident in the Developer's understanding of the Sprint.
All of the potential tasks. Sprint Planning cannot finish until all of the work is identified and estimated.
Resources
Question - How of Sprint Backlog needed to start
Domain
Product Vision